## Master Tracker
NEXUS PRIME — Master Improvement Tracker
Generated: 2026-04-06 ¦ Priority = (Impact + Risk) × (6 − Effort) ¦ Scores: ≥40 Critical 25–39 High <25 Medium/Low
ID | Name | Block | Status | Impact (1–5) | Risk (1–5) | Effort (1–5) | Priority Score | Owner Agent | Real Code Finding | Notes / API Correction | Spec File
BUG-01 | callLocalModel missing try/catch — Ollama crash unhandled | Code Debt | BUG | 4 | 5 | 1 | 45 | ORBIT | lib/ai.ts line 125-138: fetch() + res.json() with no try/catch. Ollama down = uncaught throw. | Wrap in try/catch, return '' on failure. Same pattern used everywhere else in codebase.
BUG-02 | streamRequest non-null assertion on res.body | Code Debt | BUG | 3 | 4 | 1 | 35 | ORBIT | lib/ai.ts line 86: res.body!.getReader() — crashes if body is null (e.g., 204 response). | Guard: if (!res.body) throw new Error('No response body')
BUG-03 | callAI hardcodes 'claude-opus-4-5' model string | Code Debt | BUG | 3 | 3 | 1 | 30 | ORBIT | lib/ai.ts line 159: model string hardcoded, not using aiModelRouting constants. Model drift risk. | Import and use TASK_MODELS or a dedicated constant.
BUG-04 | getSettings() reads localStorage directly, bypasses Zustand | Code Debt | BUG | 3 | 3 | 2 | 24 | ORBIT | lib/ai.ts lines 11-21: Non-reactive localStorage read. AI calls may use stale settings after in-session changes. | Accept settings as a parameter or use useStore.getState().
CP1.1 | Apply ShellPage wrapper uniformly across all 8 GA tabs | P1 Blocker | OPEN | 5 | 4 | 3 | 27 | ORBIT |  | No raw div roots. Every surface needs hero bg, panel backdrop, consistent padding. | specs/features/shell-hierarchy.md
CP1.2 | Standardize loading/empty states, buttons, segmented controls | P1 Blocker | OPEN | 5 | 4 | 3 | 27 | ORBIT |  | ShellButton, ShellBadge, skeleton spinners everywhere. No plain 'Loading...' text. | specs/features/shell-hierarchy.md
CP1.3 | HQ visual integrity pass at 1280/1440/1920px | P1 Blocker | OPEN | 4 | 3 | 2 | 28 | ORBIT |  | Fix overlap, clipping, hydration mismatch, shell drift vs login.
CP1.4a | COMMAND: inline key-input on panels missing API key | P1 Blocker | OPEN | 4 | 3 | 2 | 28 | ORBIT |  | No blank cards. Each panel shows an inline prompt to enter the key.
CP1.4b | INTEL: graceful fallback when Polymarket/SEC returns no data | P1 Blocker | OPEN | 4 | 3 | 2 | 28 | ORBIT |  | Human-readable message, not an error boundary.
CP1.4c | ALPHA: explicit no-results state with Rescan action | P1 Blocker | OPEN | 3 | 3 | 2 | 24 | ORBIT |  | BuyBot and MomentumScanner — show state, not empty table.
CP1.4d | CYBER: 'no threats' state with last-scan timestamp | P1 Blocker | OPEN | 3 | 3 | 2 | 24 | ORBIT |  | TriageView — explicit empty state.
CP1.4e | RECON: consistent results/loading/empty on all 5 sub-views | P1 Blocker | OPEN | 3 | 3 | 2 | 24 | ORBIT
CP1.4f | VAULT: onboarding prompt when no articles saved | P1 Blocker | OPEN | 3 | 2 | 1 | 25 | ORBIT |  | Explain how to save from INTEL or COMMAND.
CP2.1 | Web release rehearsal: Docker + route smoke + rollback proof | P2 Blocker | OPEN | 5 | 5 | 3 | 30 | ORBIT |  | Docker build locally, mount .env, snapshot /api/status, prove rollback. | docs/deployment/release-readiness-checklist.md
CP2.2 | Desktop isolation: NEXUS_NETWORK_MODE=isolated validation | P2 Blocker | OPEN | 4 | 5 | 3 | 27 | ORBIT |  | Confirm all panels degrade gracefully — no stuck spinners.
CP2.3 | Trust chain: checksums + signing record + SBOM (cyclonedx) | P2 Blocker | OPEN | 3 | 4 | 2 | 28 | ORBIT |  | Even if unsigned, state it explicitly and document.
CP2.4 | npm run launch:gate — single command GA gate | P2 Blocker | OPEN | 5 | 5 | 2 | 40 | ORBIT |  | type-check, lint, verify, route:integrity, eval:agent-runtime:ci, release:smoke, auth:e2e
C5 | Unit + integration tests for contract/meta layer | Testing | IN-FLIGHT | 5 | 5 | 2 | 40 | ORBIT | Zero unit tests confirmed in __tests__/. Only E2E Playwright exists. | Run npm test and npm run type-check. Both must pass. | specs/features/
A5 | Server-side prompt caching via Anthropic cache_control | Agent Intel | IN-FLIGHT | 4 | 3 | 2 | 28 | ORBIT | lib/ai.ts has client-side SYSTEM_PROMPT_CACHE but no Anthropic cache_control header. | Add cache_control:{type:'ephemeral'} in /api/ai/route.ts. Min 1024 tokens (Sonnet). 85% latency reduction possible. 1hr TTL = 2x write cost.
A6 | Wire skill governance (riskTier, approvalRequired, domainTags) | Agent Intel | IN-FLIGHT | 4 | 3 | 2 | 28 | ORBIT | lib/agent.ts has TOOL_RISK map (tier0/1/2) already. A6 extends this to Skill-level governance. | Add Skill Registry view in Settings. Pre-populate CIPHER with 5 baseline skills.
A7 | TimesFM forecasting adapter + ALPHA sparkline overlay | Agent Intel | IN-FLIGHT | 3 | 2 | 3 | 15 | FLUX |  | Add timeseries_forecast tool. ETS/ARIMA sidecar fallback. forecastAccuracy eval metric.
2B | Dead code: OfficeRoom3D props, SettingsDrawer state, prompts.ts | Code Quality | IN-FLIGHT | 3 | 2 | 2 | 20 | ORBIT |  | Run npm run check:unused (knip already in devDeps). Remove safe stale exports.
2C | Animation: replace all non-var(--t) transitions, add drawer exit | Code Quality | IN-FLIGHT | 2 | 1 | 2 | 12 | ORBIT |  | SettingsDrawer exits instantly. NotificationCenter same. Sub-tab opacity+translateY missing.
D5 | Tauri isolation E2E tests (command boundary + sidecar guards done) | Desktop | IN-FLIGHT | 4 | 4 | 3 | 24 | ORBIT |  | Guards are shipped. Remaining: tests that prove no outbound network in isolated mode.
D6 | Binary signing + SBOM generation (checksums done) | Desktop | IN-FLIGHT | 3 | 3 | 2 | 24 | ORBIT |  | Checksum workflow shipped. Remaining: code signing or explicit unsigned record + cyclonedx.
SEC-01 | Per-IP rate limiting on /api/ai (60 req/min) | Security | OPEN | 4 | 5 | 2 | 36 | CIPHER |  | Use lib/security/rateLimit.ts. Return Retry-After header on 429.
SEC-02 | Per-IP rate limiting on /api/tools write operations (10 req/min) | Security | OPEN | 4 | 5 | 2 | 36 | CIPHER |  | write_file, patch_project_file specifically.
SEC-03 | Zod validation on every /api/* route param and body field | Security | OPEN | 4 | 5 | 2 | 36 | CIPHER |  | Every query param, body field — length, type, allowed chars.
SEC-04 | RECON input validation for IP/domain fields | Security | OPEN | 4 | 5 | 2 | 36 | CIPHER |  | User could inject path traversal or redirect. Validate before any fetch URL.
SEC-05 | Add secretlint/trufflehog as pre-commit hook step | Security | OPEN | 3 | 4 | 2 | 28 | CIPHER |  | Blocks commits with API key patterns.
SEC-06 | CSP review in next.config.js + Tauri CSP audit | Security | OPEN | 3 | 4 | 2 | 28 | CIPHER |  | Confirm inline scripts blocked (nonce'd). Tauri CSP differs from Next.js CSP.
TEST-01 | Unit tests: lib/helpers.ts (fmtPrice, fmtVol, timeAgo) | Testing | OPEN | 5 | 5 | 1 | 50 | ORBIT | No unit tests exist. All testing is E2E only — inverted pyramid. | Edge cases: zero, negative, large numbers, null. Use Vitest (already in devDeps).
TEST-02 | Unit tests: lib/ragRouter.ts — routeQuery() domain routing | Testing | OPEN | 4 | 4 | 1 | 40 | ORBIT |  | Test each domain keyword set triggers correct route and not others.
TEST-03 | Unit tests: lib/liveContext.ts — compactToBudget() | Testing | OPEN | 4 | 4 | 1 | 40 | ORBIT |  | Verify maxChars respected and compacted:true set correctly.
TEST-04 | Unit tests: lib/aiModelRouting.ts — task → model mapping | Testing | OPEN | 4 | 4 | 1 | 40 | ORBIT |  | Verify each AITask maps to expected model name string.
TEST-05 | Unit tests: lib/chatCapabilityRouting.ts — detectRouteFromPrompt() | Testing | OPEN | 3 | 3 | 1 | 30 | ORBIT |  | Test each keyword set maps to expected route.
TEST-06 | Integration: Playwright — agent run loop (type → response → phases) | Testing | OPEN | 4 | 4 | 2 | 32 | ORBIT |  | Type message, confirm response appears, confirm phase strip progresses.
TEST-07 | Integration: Playwright — cron scheduler (create/toggle/delete) | Testing | OPEN | 3 | 3 | 2 | 24 | ORBIT
TEST-08 | Integration: Playwright — VAULT save from INTEL → appears | Testing | OPEN | 3 | 3 | 2 | 24 | ORBIT
TEST-09 | Integration: Playwright — notification delta alert appears | Testing | OPEN | 3 | 3 | 2 | 24 | ORBIT
TEST-10 | Eval: add user_satisfaction category (10% weight) | Testing | OPEN | 3 | 2 | 2 | 20 | JANSKY |  | Response length, no hallucinated tool names, no broken JSON.
TEST-11 | Eval: add latency metric P50/P95 for agent runs | Testing | OPEN | 3 | 2 | 2 | 20 | FLUX |  | Surface in runtime eval panel.
TEST-12 | Eval: golden-set regression (10 prompt/response pairs) | Testing | OPEN | 4 | 4 | 3 | 24 | JANSKY |  | Run weekly. Alert on >30% divergence from golden answer.
CQ-01 | TypeScript: audit all @ts-ignore and @ts-expect-error comments | Code Quality | OPEN | 3 | 3 | 2 | 24 | ORBIT |  | Each must have written justification or be resolved.
CQ-02 | TypeScript: audit all 'as any' casts | Code Quality | OPEN | 3 | 3 | 2 | 24 | ORBIT |  | Replace with proper types wherever possible.
CQ-03 | ESLint: no-console rule for production paths | Code Quality | OPEN | 2 | 2 | 1 | 20 | ORBIT |  | Replace console.log with store notifications or silent failure.
CQ-04 | ESLint: react-hooks/exhaustive-deps — fix stale dep arrays | Code Quality | OPEN | 3 | 3 | 1 | 30 | ORBIT
CQ-05 | Bundle: run npm run analyze — identify modules >200KB | Code Quality | OPEN | 3 | 2 | 1 | 25 | ORBIT | @next/bundle-analyzer already in devDependencies | Use named Three.js imports, not import * as THREE.
CQ-06 | Confirm recharts + leaflet behind dynamic() imports | Code Quality | OPEN | 3 | 2 | 1 | 25 | ORBIT |  | Not in the top-level bundle.
CQ-07 | Run npm run check:cycles (madge) — fix circular imports | Code Quality | OPEN | 3 | 3 | 1 | 30 | ORBIT | madge already in devDependencies | Circular imports are a common source of hard-to-debug Next.js issues.
PERF-01 | Polling: add navigator.onLine check before any fetch | Performance | OPEN | 3 | 2 | 1 | 25 | ORBIT |  | When offline, skip fetch and show offline badge.
PERF-02 | Polling: Intersection Observer on off-screen panels | Performance | OPEN | 3 | 2 | 2 | 20 | ORBIT |  | Pause data polling while not visible. Resume on scroll into view.
PERF-03 | Zustand: replace useStore(s=>s) full-store subscriptions | Performance | OPEN | 3 | 2 | 2 | 20 | ORBIT |  | Use narrow selectors. Prevents unnecessary re-renders on any store update.
PERF-04 | React.memo on static components that re-render on polling | Performance | OPEN | 2 | 2 | 1 | 20 | ORBIT |  | Static header elements, empty state cards.
PERF-05 | Three.js: MatrixOverlay texture regeneration optimization | Performance | OPEN | 2 | 2 | 2 | 16 | ORBIT |  | Regenerate only when scene mode changes, not every render cycle.
PERF-06 | Three.js: add performance mode toggle (disable bloom, particles) | Performance | OPEN | 2 | 1 | 2 | 12 | ORBIT |  | Disable bloom, matrix overlay, animated particles, per-desk point lights.
DATA-01 | GDELT GKG GeoJSON layer on OPS map | Data Sources | OPEN | 3 | 1 | 2 | 16 | NOVA | Free, no API key. Endpoint: api.gdeltproject.org/api/v1/gkg_geojson. Updated every 15min. | Zero-friction add. Filter by QUERY param for conflict/protest themes.
DATA-02 | World Bank API: Country Profile card in INTEL | Data Sources | OPEN | 3 | 1 | 2 | 16 | NOVA | Free, no API key. Endpoint: api.worldbank.org/v2/country/{code}/indicator/{indicator}?format=json | GDP indicator: NY.GDP.MKTP.CD. Zero-friction. 16000+ time series.
DATA-03 | BIS API: central bank rates overlay in COMMAND | Data Sources | OPEN | 3 | 1 | 2 | 16 | FLUX | Free SDMX REST API. Endpoint: stats.bis.org/api-doc/v1/. JSON/XML/CSV. No auth required. | Covers policy rates, FX reserves, credit stats.
DATA-04 | ACLED armed conflict data on OPS map | Data Sources | OPEN | 3 | 2 | 3 | 15 | NOVA | CORRECTION: Requires myACLED account + OAuth. Not key-free. Paginate at 5000 rows. | Register at acleddata.com. Add ACLED_KEY to settings. Handle OAuth token.
DATA-05 | WHO Disease Outbreak News RSS feed in INTEL | Data Sources | OPEN | 2 | 1 | 1 | 15 | NOVA | Free RSS feed. No key needed. | Parse as an RSS category in the articles loader.
DATA-06 | NASA EONET wildfire/volcano/storm events on OPS map | Data Sources | OPEN | 2 | 1 | 1 | 15 | NOVA | Free. Already know NASA FIRMS pattern from existing codebase. | Endpoint: eonet.gsfc.nasa.gov/api/v3/events
DATA-07 | CoinGecko: exponential backoff on 429 rate limit | Data Sources | OPEN | 3 | 3 | 1 | 30 | FLUX | Currently fails silently on 429. | Add exponential backoff queue.
DATA-08 | NVD CVE feed: extend to 7-day window + dedup by CVE ID | Data Sources | OPEN | 3 | 2 | 2 | 20 | CIPHER |  | Show 7-day CVE trend sparkline in CYBER.
DATA-09 | Fear & Greed 30-day history chart in ALPHA | Data Sources | OPEN | 2 | 1 | 1 | 15 | FLUX | Alternative.me supports ?limit=N param already. | Show sparkline of last 30 days.
UX-01 | Keyboard shortcuts Alt+1–8 for tab switching | UI/UX | OPEN | 3 | 1 | 2 | 16 | ORBIT |  | Show shortcuts in hover tooltip.
UX-02 | Command palette on / keypress (last 5 tabs + 5 suggestions) | UI/UX | OPEN | 3 | 2 | 3 | 15 | ORBIT |  | Reuse or extend CommandBar.
UX-03 | WCAG 2.1 AA accessibility audit on all 8 tabs | UI/UX | OPEN | 4 | 3 | 2 | 28 | ORBIT |  | Fix contrast failures. Add aria-label to all icon buttons.
UX-04 | Keyboard focus management in modals and drawers | UI/UX | OPEN | 3 | 3 | 2 | 24 | ORBIT |  | Move focus on open. Return to trigger on close.
UX-05 | prefers-reduced-motion: disable particles, bloom, matrix overlay | UI/UX | OPEN | 3 | 2 | 1 | 25 | ORBIT |  | CSS media query check.
UX-06 | 'Last updated X sec ago' indicator on all live data panels | UI/UX | OPEN | 3 | 1 | 1 | 20 | ORBIT |  | Use timeAgo() from lib/helpers.ts. Bottom-right of panel.
UX-07 | Settings drawer: section navigation tabs inside drawer | UI/UX | OPEN | 3 | 2 | 2 | 20 | ORBIT |  | General, AI, Data Sources, Security, Agent, Appearance, Advanced.
UX-08 | Settings: export + import settings JSON | UI/UX | OPEN | 3 | 1 | 2 | 16 | ORBIT |  | Export redacts all key fields (replace with ***SET***).
UX-09 | Notification: mark all read + category filter row | UI/UX | OPEN | 2 | 1 | 1 | 15 | ORBIT |  | MARKET, THREAT, AGENT, SYSTEM categories.
UX-10 | Voice input: microphone button on HQ chat (Chrome/Edge only) | UI/UX | FUTURE | 2 | 1 | 2 | 12 | ORBIT | Web Speech API: Chrome/Edge only. Firefox NOT supported. Audio sent to Google servers. | Add voiceInputEnabled toggle. Default off. Show browser compat warning.
AI-01 | Agent detection: bigram/phrase matching in detectAgent() | Agent Intel | OPEN | 3 | 2 | 2 | 20 | JANSKY |  | 'security scan' scores higher for CIPHER than 'scan' alone.
AI-02 | Agent pin: parse @ORBIT: or @NOVA: prefix before detection | Agent Intel | OPEN | 3 | 1 | 2 | 16 | JANSKY
AI-03 | Memory: recall_by_query TF-IDF search over IndexedDB | Agent Intel | OPEN | 3 | 2 | 3 | 15 | NOVA |  | No external API. Client-side TF-IDF index.
AI-04 | Memory: 30-day age-out policy with cold archive | Agent Intel | OPEN | 2 | 1 | 2 | 12 | NOVA |  | Entries without reinforcement flag → cold archive after 30 days.
AI-05 | RAG: confidence score + multi-domain on low confidence (<0.4) | Agent Intel | OPEN | 3 | 2 | 2 | 20 | JANSKY
AI-06 | RAG: add geopolitical + healthcare domain routes | Agent Intel | OPEN | 3 | 1 | 2 | 16 | NOVA |  | geopolitical: war/conflict/sanctions/NATO. healthcare: FDA/pharma/WHO.
DX-01 | Update docs/architecture.md to reflect 3D office, RAG, skill engine | Dev XP | OPEN | 3 | 2 | 2 | 20 | JANSKY |  | Current doc predates 3D office, operational profiles, RAG router.
DX-02 | JSDoc on all exports in lib/agent.ts, lib/ai.ts, lib/liveContext.ts | Dev XP | OPEN | 2 | 1 | 2 | 12 | ORBIT |  | These are the most complex files new contributors read first.
DX-03 | Add npm run snapshot:api — API response shape diff tool | Dev XP | OPEN | 3 | 2 | 2 | 20 | ORBIT |  | Snapshot shapes. Alert on breaking API contract changes.
V0.1 | Simulated telemetry generator + replay mode for /internal/vehicle | Vehicle | FUTURE | 2 | 1 | 3 | 9 | NOVA |  | Lets UI be built and tested without a live drone.
V0.2 | Standardize flight telemetry schema (heartbeat, GPS, battery, mode) | Vehicle | FUTURE | 2 | 1 | 2 | 12 | JANSKY
V0.3 | Archive flight-log artifacts into VAULT conventions | Vehicle | FUTURE | 2 | 1 | 2 | 12 | JANSKY
V1.1 | F450 bench bring-up checklist in VAULT | Vehicle | FUTURE | 2 | 2 | 2 | 16 | JANSKY |  | Props-off validation, RC, GPS, orientation, failsafe confirmation.
V1.2 | Passive telemetry bridge: flight stack → OPS map (read-only) | Vehicle | FUTURE | 3 | 2 | 4 | 10 | ORBIT |  | Nexus NEVER sends commands. Real-time GPS/battery/mode on OPS Leaflet map.
EXT-01 | Adversarial eval category (loophole-style prompts blocked/escalated) | B11 Ecosystem | OPEN | 4 | 4 | 3 | 24 | ORBIT |  | Add adversarial category to eval-agent-runtime.js. 10 adversarial prompts, CI gate --min-category adversarial=90.
EXT-02 | Constraint consistency checker — detect contradiction with prior decisions | B11 Ecosystem | OPEN | 4 | 4 | 3 | 24 | JANSKY |  | check_precedent_conflict() tool. Session-scoped precedent log in IndexedDB. Escalate to HUD on conflict.
EXT-03 | Decision diff view in VAULT — timeline + git-style diffs per session | B11 Ecosystem | OPEN | 3 | 2 | 3 | 15 | ORBIT |  | Session Decisions panel in VAULT. Line-level diff using fhi/flo colors. Export as markdown for handoff.
EXT-04 | Dynamic precedent binding — reinforced entries block auto-run contradictions | B11 Ecosystem | OPEN | 3 | 3 | 2 | 24 | ORBIT |  | Add reinforced: boolean to KnowledgeEntry. Reinforced entries trigger human-gate before any conflicting write.
EXT-05 | Synthetic golden-set generator — config-driven test cases + LLM judge validation | B11 Ecosystem | OPEN | 5 | 4 | 3 | 27 | ORBIT |  | scripts/gen-golden-set.mjs. YAML config → 20-50 test cases. LLM judge scores <70 flagged for human review. Output to __tests__/golden/.
EXT-06 | LLM-as-judge eval scorer — four-axis quality scoring in CI + HUD | B11 Ecosystem | OPEN | 5 | 4 | 3 | 27 | ORBIT |  | Add judge category to eval harness. Axes: accuracy, relevance, grounding, safe behavior (0–25 each). CI gate: --min-category judge=75.
EXT-07 | Dry-run / preview mode for missions — shimmed writes show plan before committing | B11 Ecosystem | OPEN | 4 | 3 | 3 | 21 | ORBIT |  | Preview Run button in HQ scheduler. Shims write tools, executes reads normally. Shows tool list, token cost, projected artifacts, precedent conflicts.
EXT-08 | Dependency-aware memory recall — correlated entries alongside primary match | B11 Ecosystem | OPEN | 3 | 2 | 2 | 20 | ORBIT |  | Extends recall_by_query (AI-03). Returns related[] array of correlated entries (shared tag/entity or recorded within 5 min).
EXT-09 | Validator pipeline for agent writes — auto type-check + lint + smoke post-write | B11 Ecosystem | OPEN | 5 | 5 | 3 | 30 | ORBIT |  | Extend /api/verify chain to run after every write_file or patch_project_file. Fail → quarantine artifact with verificationFailed flag + HUD alert.
EXT-10 | n8n template patterns — NOVA multi-query, FLUX whale alerts, startup intel mission | B11 Ecosystem | OPEN | 3 | 2 | 2 | 20 | NOVA |  | Map Open Deep Research (2883) query-expansion to NOVA. Map crypto alpha (5632) to FLUX. Map startup intel (4792) to weekly NOVA scheduled mission.

## Testing Plan
NEXUS PRIME — Testing Strategy (Pyramid-First)
Current state: INVERTED PYRAMID — Zero unit tests, some E2E only. Fix by building bottom-up.
Test ID | Target | Test Type | Framework | Coverage Target | Priority | Example Test Case | Status
T-U01 | lib/helpers.ts — fmtPrice() | Unit | Vitest | 100% | Critical | expect(fmtPrice(0)).toBe('$0.00'); expect(fmtPrice(-1.5)).toBe('-$1.50'); expect(fmtPrice(null)).toBe('—') | OPEN
T-U02 | lib/helpers.ts — fmtVol() | Unit | Vitest | 100% | Critical | expect(fmtVol(1000)).toBe('1.0K'); expect(fmtVol(1500000)).toBe('1.5M') | OPEN
T-U03 | lib/helpers.ts — timeAgo() | Unit | Vitest | 100% | Critical | expect(timeAgo(Date.now()-60000)).toMatch(/1 min/) | OPEN
T-U04 | lib/ragRouter.ts — routeQuery() | Unit | Vitest | 90% | Critical | expect(routeQuery('CVE exploit ransomware').domain).toBe('security') | OPEN
T-U05 | lib/liveContext.ts — compactToBudget() | Unit | Vitest | 90% | Critical | expect(compactToBudget(longStr, 100).compacted).toBe(true) | OPEN
T-U06 | lib/aiModelRouting.ts — task→model mapping | Unit | Vitest | 100% | High | expect(TASK_MODELS['research']).toBeDefined() | OPEN
T-U07 | lib/chatCapabilityRouting.ts — detectRouteFromPrompt() | Unit | Vitest | 90% | High | expect(detectRouteFromPrompt('check CVEs')).toBe('/cyber') | OPEN
T-U08 | lib/ai.ts — callLocalModel() error handling | Unit | Vitest | 80% | Critical | Mock fetch to throw → expect function to return '' not throw | OPEN
T-U09 | lib/ai.ts — getSettings() fallback when localStorage missing | Unit | Vitest | 80% | High | Mock localStorage.getItem to throw → expect DEFAULT_SETTINGS returned | OPEN
T-U10 | store/useStore — Zustand state shape validation | Unit | Vitest | 70% | Medium | Verify all required fields present after store init | OPEN
T-I01 | HQ chat: type message → response → phase strip | Integration | Playwright | Key path | Critical | Fill input, click send, waitFor('.phase-strip .done'), assertResponse non-empty | OPEN
T-I02 | Cron scheduler: create → toggle on → verify in list → delete | Integration | Playwright | Key path | High | Full CRUD flow via UI | OPEN
T-I03 | VAULT: save article from INTEL → navigate to VAULT → appears | Integration | Playwright | Key path | High | Click bookmark in INTEL, navigate, assert article title present | OPEN
T-I04 | Notification: delta alert appears in notification center | Integration | Playwright | Key path | High | Trigger price delta, open notification center, assert notification present | OPEN
T-I05 | Settings: export JSON → verify no keys present | Integration | Playwright | Security | High | Click export, parse JSON, assert no raw API key values | OPEN
T-I06 | RECON: IP input validation rejects path traversal | Integration | Playwright | Security | High | Enter '../etc/passwd', expect validation error, no fetch attempted | OPEN
T-E01 | Auth E2E: valid login, invalid, stale session, refresh, logout | E2E | Playwright | Full flow | Critical | Already done — maintain and run on every push | CLOSED
T-E02 | Route contract: /, /home, beta aliases, GA nav all resolve | E2E | Playwright | Full flow | Critical | Already done — maintain and run on every push | CLOSED
T-E03 | HQ shell: office renders, agent markers visible, splitter works | E2E | Playwright | Key path | High | Navigate to /home, assert canvas present, assert 5 agent markers | OPEN
T-E04 | Offline: navigator.onLine=false → all panels show offline badge | E2E | Playwright | Resilience | Medium | Simulate offline via CDP, navigate, assert all panels degrade gracefully | OPEN
T-R01 | Eval: safety category ≥ 80% | Eval/CI | eval-agent-runtime.js | 80%+ | Critical | npm run eval:agent-runtime:ci — must pass on every merge to main | PARTIAL
T-R02 | Eval: reliability category ≥ 80% | Eval/CI | eval-agent-runtime.js | 80%+ | Critical | Same as above | PARTIAL
T-R03 | Eval: user_satisfaction category (add — target 75%) | Eval/CI | eval-agent-runtime.js | 75%+ | Medium | New category: response length, no hallucinated tools, no broken JSON | OPEN
T-R04 | Eval: latency P50 <3s, P95 <8s for agent runs | Eval/CI | eval-agent-runtime.js | P50<3s | Medium | Add timing instrumentation to agent loop runs | OPEN
T-R05 | Golden-set: 10 prompt/response pairs, weekly regression | Eval/CI | Custom script | 0% diverge | High | Alert if any response diverges >30% from golden answer (cosine similarity) | OPEN

## API Reference
NEXUS PRIME — External API Reference (Verified 2026-04)
API / Source | Status | Key Required | Endpoint Pattern | Rate Limit | Tab Target | Notes
CoinGecko | LIVE | cgKey (optional) | api.coingecko.com/api/v3 | 30 calls/min free | COMMAND / ALPHA | Add exponential backoff on 429. Currently fails silently.
Alternative.me F&G | LIVE | None | api.alternative.me/fng/?limit=N | Generous | ALPHA / COMMAND | ?limit=30 gives 30-day history for history chart.
USGS Earthquakes | LIVE | None | earthquake.usgs.gov/.../all_day.geojson | Unlimited | OPS
OpenSky Network | LIVE | None | opensky-network.org/api/states/all | 10s interval anon | OPS
NOAA SWPC | LIVE | None | services.swpc.noaa.gov/json | Unlimited | OPS
NASA FIRMS | LIVE | firmsKey | firms.modaps.eosdis.nasa.gov/api | API key required | OPS
NVD NIST CVEs | LIVE | nvdKey (optional) | services.nvd.nist.gov/rest/json/cves/2.0 | 5 req/30s w/ key | CYBER | Extend to 7-day window. Dedup by CVE ID.
AlienVault OTX | LIVE | otxKey | /api/threat-intel (server-side proxy) | Needs key | CYBER
Polymarket Gamma | LIVE | None | gamma-api.polymarket.com/events | Unlimited | INTEL
FRED (St. Louis Fed) | LIVE | fredKey | api.stlouisfed.org/fred/series/observations | Needs key | INTEL
The Guardian | LIVE | guardianKey | content.guardianapis.com/search | Needs key | INTEL
gpsjam.org | LIVE | None | gpsjam.org/map-stats | Unlimited | OPS
aisstream.io | LIVE | aisstreamKey | WebSocket: stream.aisstream.io/v0/stream | Key required | OPS | Read-only WebSocket.
Firecrawl | LIVE | firecrawlKey | api.firecrawl.dev | Key required | ALPHA (AI thesis)
Finnhub | LIVE | finnhubKey | finnhub.io/api/v1 | 60 calls/min free | ALPHA
GDELT GKG GeoJSON | ADD NOW | None ✓ | api.gdeltproject.org/api/v1/gkg_geojson | Updated every 15min | OPS (new layer) | Zero-friction. Filter with ?QUERY= for conflict/protest themes.
World Bank Indicators | ADD NOW | None ✓ | api.worldbank.org/v2/country/{code}/indicator/{indicator}?format=json | Unlimited | INTEL (Country Profile) | No key ever needed. 16000+ indicators. GDP: NY.GDP.MKTP.CD
BIS Stats API | ADD NOW | None ✓ | stats.bis.org/api-doc/v1/ (SDMX REST) | Open, attribution required | COMMAND (macro) | JSON/XML/CSV. Policy rates, FX reserves, credit stats.
WHO Outbreak News RSS | ADD NOW | None ✓ | who.int/rss-feeds/news-releases-en.xml | Unlimited | INTEL (health feed) | Parse as RSS category. No key.
NASA EONET | ADD NOW | None ✓ | eonet.gsfc.nasa.gov/api/v3/events | Unlimited | OPS (events layer) | Wildfire, volcano, storm. Same pattern as FIRMS.
ACLED | SIGNUP NEEDED | OAuth token | api.acleddata.com/acled/read | 5000 rows/page | OPS (conflict) | CORRECTION: Requires myACLED account registration. Not key-free. Register at acleddata.com
UN Comtrade | SIGNUP NEEDED | API key | comtradeapi.un.org/data/v1/get | Free tier available | INTEL (trade) | Registration required for API key.
Web Speech API | BROWSER LIMIT | None (browser) | window.SpeechRecognition | N/A | HQ chat (voice) | CRITICAL: Chrome/Edge only. Firefox NOT supported. Audio sent to Google servers. Add compat warning.

## Tech Debt Scores
NEXUS PRIME — Tech Debt Priority Scores
Priority = (Impact + Risk) × (6 − Effort) ¦ ≥40 = Critical (fix immediately) ¦ 25–39 = High ¦ <25 = Medium/Low
ID | Debt Item | Type | Impact (1–5) | Risk (1–5) | Effort (1–5) | Priority Score | Remediation
BUG-01 | callLocalModel() missing try/catch around fetch + res.json() | Code | 4 | 5 | 1 | 45 | Wrap in try/catch, return '' on failure. Same pattern used everywhere else in codebase.
TEST | Zero unit tests for lib/ (fmtPrice, routeQuery, compactToBudget, etc.) | Test | 5 | 5 | 2 | 40 | Add Vitest unit tests. Already in devDeps. Start with helpers.ts, ragRouter.ts.
BUG-02 | streamRequest non-null assertion res.body!.getReader() | Code | 3 | 4 | 1 | 35 | Guard: if (!res.body) throw new Error('No response body')
SEC | No per-IP rate limiting on /api/ai or /api/tools | Security | 4 | 5 | 2 | 36 | Add rateLimit.ts middleware. 60 req/min for ai, 10 req/min for write tools.
BUG-03 | callAI() hardcodes 'claude-opus-4-5' model string | Code | 3 | 3 | 1 | 30 | Use aiModelRouting constant. Prevents silent model drift.
BUG-04 | getSettings() reads localStorage directly, bypasses Zustand reactivity | Code | 3 | 3 | 2 | 24 | Pass settings as parameter or use useStore.getState().
ARCH | Testing pyramid inverted: zero unit tests, some E2E only | Architecture | 4 | 4 | 2 | 32 | Build bottom-up: unit → integration → E2E. See Testing Plan sheet.
SEC-02 | No Zod validation on /api/* route params and body fields | Security | 4 | 5 | 2 | 36 | Add Zod schemas to every route handler.
SEC-03 | RECON IP/domain inputs not validated before use in fetch URLs | Security | 4 | 5 | 2 | 36 | Validate format and whitelist allowed patterns before fetch.
P1 | ShellPage hierarchy missing on multiple GA tabs | Architecture | 5 | 4 | 3 | 27 | Apply ShellPage + ShellSurface + ShellButton uniformly. P1 GA blocker.
DEAD | Dead props in OfficeRoom3D, stale state in SettingsDrawer | Code | 3 | 2 | 2 | 20 | Run knip (npm run check:unused). Remove safe stale exports.
POLL | No navigator.onLine check before any polling fetch | Code | 3 | 2 | 1 | 25 | Skip fetch when offline. Show offline badge.
ZUSTAND | Full store subscriptions useStore(s=>s) in some components | Code | 3 | 2 | 2 | 20 | Replace with narrow selectors to prevent unnecessary re-renders.
BUNDLE | Three.js imported as * (import * as THREE) | Code | 3 | 2 | 1 | 25 | Use named imports. Significant bundle size reduction.
ANIM | Animation values not using var(--t) consistently | Code | 2 | 1 | 2 | 12 | Grep for transition: and duration- values. Replace with var(--t).
DOC | docs/architecture.md predates 3D office, RAG router, skill engine | Documentation | 3 | 2 | 2 | 20 | Update to reflect current architecture.

## Phase Roadmap
NEXUS PRIME — Phase Roadmap
Phase | Name | Items | Gate Criteria | Status
P0 | Pre-GA Blockers | CP0.1–CP0.4 | Auth E2E pass, regression sweep clear, fresh-runtime smoke green, route contract verified | CLOSED ✓
P1 | Cinematic IA Completion | CP1.1–CP1.4f | ShellPage on all 8 tabs, zero blank cards, zero plain 'Loading...' text, HQ clean at 1280/1440/1920px | IN PROGRESS
P2 | Release Engineering | CP2.1–CP2.4 | Docker build proven, desktop isolated, checksums generated, npm run launch:gate exits 0 | IN PROGRESS
In-Flight | Parallel track (non-blocking) | C5, A5, A6, A7, 2B, 2C, D5, D6 | All 8 items marked done with proof. Type-check passes. | IN PROGRESS
Block 2 | Code Quality + Tech Debt | CQ-01–07, BUG-01–04 | knip shows zero unused exports, no @ts-ignore without comment, bundle analyzed, bugs fixed | OPEN
Block 3 | Agent Intelligence | A5–A7, AI-01–06 | Prompt caching live, skill governance wired, CIPHER baseline populated, RAG routes expanded | OPEN
Block 4 | UI/UX | UX-01–10 | WCAG 2.1 AA audit passes, keyboard shortcuts work, settings sectioned, accessibility complete | OPEN
Block 5 | Data Sources | DATA-01–09 | GDELT + World Bank + BIS + WHO + EONET wired. CoinGecko backoff added. ACLED registered. | OPEN
Block 6 | Security Hardening | SEC-01–06 | Rate limiting live on /api/ai and /api/tools, Zod on all routes, secretlint in pre-commit | OPEN
Block 7 | Performance | PERF-01–06 | Polling respects runtimeConfig, narrow Zustand selectors, Three.js perf mode available | OPEN
Block 8 | Testing | TEST-01–12 + T-U/I/E/R | Unit tests exist for all lib/ functions, integration tests for key flows, eval categories expanded | OPEN
Block 9 | Developer Experience | DX-01–03 | architecture.md updated, JSDoc on lib/, snapshot:api script added | OPEN
Block 10 | New Capabilities | UX-10, DATA features | Voice input (Chrome/Edge), keyword alerts, world event map, geo risk scoreboard | FUTURE
Vehicle | Drone / Telemetry Lane | V0.1–V1.2 | Simulated telemetry, flight schema, VAULT archiving, F450 checklist, passive bridge | FUTURE